## Sheet1
Year 3 Final Year Project
Supervisor: Dr Hermawan Nugroho | [8 empty] | Student Name: Koay Xian Cong | [11 empty] | Legends: | Error Bars for Uncertainty: | [6 empty] | Moderator Meeting Week:
Moderator: Prof T. Nandha Kumar | [8 empty] | Student ID: 20418760 | [12 empty] | Submission Dateline: | [6 empty] | Project Milestone:
Project Code: HN-BEng-23-01
Tasks | Autumn Semester | [11 empty] | Study Week |  |  | Exam |  | Sem Break |  |  | CNY Break | Spring Semester | [6 empty] | HR Break |  |  |  | Study Week
| Sept | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May
| WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14 | WEEK 15 | WEEK 16 | WEEK 17 | WEEK 18 | WEEK 19 | WEEK 20 | WEEK 21 | WEEK 22 | WEEK 23 | WEEK 24 | WEEK 25 | WEEK 26 | WEEK 27 | WEEK 28 | WEEK 29 | WEEK 30 | WEEK 31 | WEEK 32 | WEEK 33 | WEEK 34 | WEEK 35 | WEEK 36 | WEEK 37
Project Planning | Dec WEEK 16: Study Week; Jan WEEK 19: Exam; Jan WEEK 21: Sem Break; Feb WEEK 24: CNY Break; Apr WEEK 32: HR Break; May WEEK 36: Study Week
Hazard Identification, Risk Assessment, Risk Control Form (HIRARC) Form | bar: Sept WEEK 4
FYP Briefing and Discussion on Project Specification | bar: Sept WEEK 4 to Oct WEEK 6
Hardware Inspection and Sensor Component Research | bar: Oct WEEK 5 to Oct WEEK 6
Software, Tools and Application Research | bar: Oct WEEK 5 to Oct WEEK 6
Finalising Project Objectives and Project Specification | bar: Oct WEEK 6
Hardware and Software Research and Purchase Cost Estimation | bar: Oct WEEK 6 to Oct WEEK 7
Purchase Requisition | bar: Oct WEEK 7
Lab Space Booking | bar: Oct WEEK 7
Obtaining Ethical Approval | bar: Oct WEEK 7
Writing Project Outline and Planning Report | bar: Oct WEEK 7 to Oct WEEK 9
Submission of Project Outline and Planning Report | bar: Oct WEEK 9
Research and Literature Review
Researching of Common Application of Edge Computing | bar: Sept WEEK 4 to Oct WEEK 6
Literature Review of Emotion Recognition using ECG | bar: Oct WEEK 6 to Oct WEEK 9
Literature Review of Common Heart Disease | bar: Oct WEEK 6 to Oct WEEK 9
Literature Review of Heart Disease Detection using Machine Learning and Deep Learning | bar: Oct WEEK 6 to Oct WEEK 9
Literature Review of Heart Disease Prediction Model | bar: Oct WEEK 6 to Oct WEEK 9
Literature Review of STM32MP157F DK Edge Computing Device and Application | bar: Oct WEEK 6 to Oct WEEK 9
Literature Review of Software Tools, Model and Architecture for Edge Computing | bar: Oct WEEK 6 to Oct WEEK 9
Design Solution/Application
Research and Learning the Function of STM32MP157F DK Edge Computer | bar: Oct WEEK 8 to Oct WEEK 9
Installing Virtual Machine to Set Up STM32 Software to Flash OS into the Edge Computer | bar: Oct WEEK 9 to Nov WEEK 10
Installing STM32 Cube Programmer in Ubuntu OS | bar: Nov WEEK 10
Coding Program to Test Functions of Edge Computer | bar: Nov WEEK 10
Integrating Heart Monitoring Sensor onto the Edge Computer | bar: Nov WEEK 10 to Nov WEEK 11
Coding Program to Test Sensors and Perform Experiments to Ensure Accurate Measurements of Sensors | bar: Nov WEEK 11 to Nov WEEK 13
Designing Wearables of that can be Integrated with Heart Disease Detection and Prediction Solution (Optional) | bar: Nov WEEK 12 to Dec WEEK 14
Development of AI Model
Setting Up Environment to Deploy Heart Disease Detection and Prediction Model | bar: Dec WEEK 14
Coding Program to Develop Emotion Recognition Model | bar: Dec WEEK 14 to Dec WEEK 15; Jan WEEK 22
Coding Program to Develop Heart Disease Prediction Model | bar: Dec WEEK 14 to Dec WEEK 15; Jan WEEK 22
Coding Program to Connect Sensor with AI Model | bar: Jan WEEK 22 to Feb WEEK 23; Feb WEEK 25
Coding Program to Display Prediction Output on the LCD Display (Optional) | bar: Feb WEEK 25 to Feb WEEK 26
Developing User Interface to Monitor Heart Disease and Data Collected from Sensor (Optional) | bar: Feb WEEK 26 to Mar WEEK 28
Debugging Code to Solve Bugs Found, Improvement of Code/Model | bar: Mar WEEK 27 to Mar WEEK 28
Deployment of Model and Sensor into Edge and Cloud Computer
Combining both Software and Hardware Developed into Wearables (Optional) | bar: Mar WEEK 27 to Mar WEEK 29
Deploying Heart Disease Prediction Model Developed onto Cloud Computer | bar: Mar WEEK 27 to Mar WEEK 30
Deploying Emotion Recognition Model Developed onto Edge Computer | bar: Mar WEEK 27 to Mar WEEK 30
Performing Testing on Real Live User | bar: Mar WEEK 29 to Mar WEEK 30
Obtaining User Experience, Feedback and Model Prediction Result | bar: Mar WEEK 29 to Apr WEEK 31
Performance Improvement and Solving Bugs | bar: Mar WEEK 30 to Apr WEEK 31
Thesis, Documents and Presentation
Writing Sections of Draft Thesis | bar: Mar WEEK 29 to Apr WEEK 31
Draft Typed Thesis Submission | bar: Apr WEEK 31
Writing Sections of Final Thesis | bar: Apr WEEK 31; Apr WEEK 33 to Apr WEEK 35
Final Thesis, Logbook, Code and Miscellaneous Submission | bar: Apr WEEK 35
Preparation of Presentation | bar: Apr WEEK 35
Presentation
Return of Project Items